## Requirement
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: |  |  |  | PROJECT ID:
PROJECT SPONSOR: |  |  |  | PROJECT TITLE:
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | BUSINESS OBJECTIVE | DELIVERABLE(S | VERFICATION | VALIDATION
REQ-001 | Mandatory | Unauthorized/Authorized cards should work appropriately | Samruddhi
REQ-002 | Mandatory | User should have ability to quit any time in between the transaction. | Kajal
REQ-003 | Mandatory | ATM should have facility to accept valid PIN from user | Disha
REQ-004 | Should have | ATM Home screen should show the name of user whose account is linked to ATM card | Shruti
REQ-005 | Should have | ATM should have ability to clear the user input | Palak
REQ-006 | Nice to have | UI should greet welcome message based on day time. | Archana
REQ-007 | Nice to have | ATM show show aapropriate error in case on internet issues or server problems | Aparna

## TestCases
Test Case Template
| Test Case ID: REQ02_TC001 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User should have ability to pull back the card and return to the main page | Test Execution date: 13/08/2020
Description:User may pull back the card accidently then user should be redirected to main page
Pre-conditions: | User has a valid card
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User pulls the card back | Valid Card | Alert msg that card is taken out should be displayed and return to main page | Blocked as it is not developed | Blocked
3
4
Test Case Template
| Test Case ID: REQ02_TC002 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User may not enter pin so it should return to the main page | Test Execution date:13/08/2020
Description:User may forget to enter pin then user should be redirected to main page
Pre-conditions: | User has a valid card
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User doesnot enter the pin and waits for a specified time |  | It should display please enter pin msgand after waiting for specified time user should be redirected to main page | Blocked as it is not developed | Blocked
3
4
Test Case Template
| Test Case ID: REQ02_TC003 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User enters pin and then he clicks on exit. so it should return to the main page but continue button is not enabled | Test Execution date: 13/08/2020
Description:User may forget to enter pin then user should be redirected to main page after some specified time interval
Pre-conditions: | User has a valid card
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters the pin | Pin | Machine accepts the pin and continue button should be Enabled | ..\Documents\pin.docx | Fail
3 | User clicks on exit button |  | User should be redirected to main page
4
5
6
Test Case Template
| Test Case ID: REQ02_TC004 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User inserts valid card, enters pin, transaction type as debit , amount and then he clicks on exit. so it should return to the main page | Test Execution date: 13/08/2020
Description: User inserts valid card, enters pin, transaction type as debit, amount and then he clicks on exit. so it should take the money back and return to the main page
Pre-conditions: | User has a valid card and pin
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters the pin | Pin | Machine accepts the pin and continue button is enabled | ..\Documents\pin.docx | Pass
3 | User clicks continue and enters the type of transaction | Debit | User is asked for amount | Blocked as it is not developed | Blocked
4 | User enters the amount and clicks on confirm | amount | Machine gives the amount to the user | Blocked as it is not developed | Blocked
5 | user clicks exit before transaction is completed |  | User is asked to insert money if not present and user is redirected to the home page | Blocked as it is not developed | Blocked
6
Test Case Template
| Test Case ID: REQ02_TC005 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User inserts valid card, enters pin, transaction type as credit , amount and then he clicks on exit. so it should return to the main page | Test Execution date: 13/08/2020
Description: User inserts valid card, enters pin, transaction type as credit , amount and then he clicks on exit. so it should return to the main page and return the money back to the user
Pre-conditions: | User has a valid card and pin
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters the pin | Pin | Machine accepts the pin and continue button is enabled | ..\Documents\pin.docx | Pass
3 | User clicks continue and enters the type of transaction as debit | Credit | User is asked for amount | Blocked as it is not developed | Blocked
4 | User enters the amount and clicks confirm | amount | Machine asks the user to enter the cash | Blocked as it is not developed | Blocked
5 | User dosnot put the cash clicks on exit button |  | Alert msg is displayed that you did not enter the cash anduser is redirected to home page | Blocked as it is not developed | Blocked
Test Case Template
| Test Case ID: REQ02_TC006 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User inserts valid card, enters pin, transaction type as credit , amount,cash and then he clicks on exit. so it should return to the main page | Test Execution date: 13/08/2020
Description: User inserts valid card, enters pin, transaction type as credit , amount,cash and then he clicks on exit. so it should return to the main page and return the money back to the user
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters the pin | Pin | Machine accepts the pin and moves to transaction page | ..\Documents\pin.docx | Pass
3 | User enter type of transaction | Credit | User is asked for amount | Blocked as it is not developed | Blocked
4 | User enters the amount | amount | Machine asks the user to enter the cash | Blocked as it is not developed | Blocked
5 | User deposits the cash in the machine | Cash | Machine processes the transaction | Blocked as it is not developed | Blocked
6 | User clicks exit when transaction is in progress |  | Machine should cancel the transaction and return the money | Blocked as it is not developed | Blocked
Test Case Template
| Test Case ID: REQ02_TC007 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User doenot enters the transaction type and waits for a specified time | Test Execution date: 13/08/2020
Description:User may forget to enter the transaction type so he should be redirected to main page after waiting for some time
Pre-conditions: | User has a valid card and pin
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters the pin | Pin | Machine accepts the pin and moves to transaction page | ..\Documents\pin.docx | Pass
3 | User doesnot enter type of transaction and waits for a specified time |  | Alert message will be displayed that you did not enter the transaction type and home page is displayed after some time | Blocked as it is not developed | Blocked
Test Case Template
| Test Case ID: REQ02_TC008 | Test Designed by: Kajal Kankariya
| Test Priority (Low/Medium/High): High | Test Designed date: 11/08/2020
| Module Name: Home Page | Test Executed by: Kajal Kankariya
| Test Title: User may enter incorrect pin and then click on eit | Test Execution date: 13/08/2020
Description: User may enter incorrect pin and then click on eit
Pre-conditions: | User has a valid card and pin
Step | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Remarks
1 | User inserts the card in the atm machine | Valid card | Atm should display the enter pin screen | ..\Documents\welcome.docx | Pass
2 | User enters incorrect pin | invalid pin | Alert message should be displayed that pin is incorrect | ..\Documents\incorrectpin.docx | Pass
3 | User clicks on exit |  | Home page is displayed | Blocked as not developed | Blocked

## Bugs
Fields | Label | Value
Bug ID | ID number | #123
| Name | Continue button is not enabled
| Reporter | Kajal Kankariya
| Submit Date | 13/08/2020
Bug overview | Summary | When user inserts card and enters the pin continue button is not enabled
| URL | ..\Documents\pin.docx
| Screenshot | ..\Documents\pin.docx
Environment | Platform | Macintosh
| Operating System | OS X 10.12.0
| Browser | Chrome 53
Bug details | Steps to reproduce | REQ02_TC003 1. User inserts the card 2. User enters pin 3. User clicks on continue
| Expected result | Continue button should be enabled
| Actual result | Continue button is not enabled
| Description | Continue button should be enabled so that user can do transaction
Bug tracking | Severity | Major
| Assigned to | /
| Priority | High
Notes | Notes/Remarks | /

## Kajal_TestExecution_Report
Test Report
Iteration/ Cycle
EXECUTED | PASSED | 0
| FAILED | 1
| (Total) TESTS EXECUTED (PASSED + FAILED+BLOCKED) |  | 8
PENDING |  |  | 0
IN PROGRESS |  |  | 0
BLOCKED |  |  | 7
(Sub-Total) TEST PLANNED |  |  | 8
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
DEFERRED |  |  | 8
Feature/Components | # Tests Planned | % Tests Executed | % Tests Passed | # Deferred/ blocked | Status
<Name of feature/type> | <No of planned test cases > | <Percentage of executed test cases> | <Percentage test cases of executed test case that passed> | <No of Deferred test cases > | <Green/ Red/ Yellow>
User should have ability to quit any time in between the transaction. | 8 | 8 | 0 | 7
Defect ID | Description | Test Case ID | Originator | Priority | Serverity | Status
<Defect ID in defect tracking tool> | < Description of Defect and step to preproduce the defect> | < Test case ID> | <Originator of Defect> |  |  | <Open Close>
#123 | When user inserts card and enters the pin continue button is not enabled | REQ02_TC003 |  | P1 |  | Open